## Sheet1
529 | Pick which 3 activities are the responsibility of the Scrum Master in Scrum. | Facilitate meetings, Remove impediments, Champion Scrum
413 | How does an organization know that a product built through Scrum is successful? | By releasing often, and updating key performance indicators (KPIs) on value after every release and feeding this information back into work on the Product Backlog.
2388 | As a Product Owner, if you had access to the following individuals, what sources might you consult with when considering the value of a product? Choose all that apply. | CEO, Customers and Prospects, Market research results and analyst reports, Sales Executive or Sales Leader, Development Team
395 | What are two typical activities for a Product Owner in a Sprint? | Work with the Developers on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
2412 | Which of the following practices might help the Product Owner minimize waste in developing and sustaining the Product Backlog? Choose 2 answers. | Write or cause Product Backlog items to be written clearly, and with a little ambiguity as possible., Only fully describe Product Backlog items when it seems sure that they are likely to be implemented.
513 | The product Increment must be released to production at the end of each Sprint. | FALSE
479 | Which TWO things do NOT occur in the first Sprint? | Define the complete architecture., Finalize the complete Product Backlog.
448 | Suppose the current release will be complete after 6 two-week sprints. A team member is insisting that the Product Owner write the acceptance test cases for the entire release. How should the Scrum Master respond? | Explain that stories should only be discussed in detail prior to development. Elaborating stories not in the next couple of iterations is wasteful.
460 | Pick three topics that can be addressed in the Sprint Retrospective? | Team Working Agreement., Definition of Done., Team Dynamics.
489 | To truly adopt Scrum, you must pick and choose which roles, artifacts, events, and rules are right for your organization. | FALSE
507 | The Product Owner should be with the Developers full time. | FALSE
534 | Which of the following statements is NOT true? | The Product Backlog is complete when the final product Increment is considered Done.
536 | Please select which statement is the MOST accurate: | Refinement is a part-time activity during a Sprint between the Product Owner and the Developers.
2052 | You are a Product Owner working on an agile software development project and you have brought all the Scrum team members together for the first Iteration Planning meeting. You read the user stories to the team, and they have provided estimates to complete these user stories. You have promised to leave them alone during the iteration to get the work done and they have agreed to complete the work 100% according to the definition of done. What is this an example of? | Reciprocal commitment
520 | Software dependencies can influence how the product owner orders Product Backlog items. | FALSE
3955 | Who should do the legwork of gathering the marketplace data for the Product Owner? | It does not matter who does the legwork
589 | Scrum does not scale to large teams. | FALSE
528 | Who is responsible for the change management in Scrum projects? | Product Owner
510 | The Product Owner actively asks for stakeholder input into the Product Backlog. | TRUE
2426 | Product Owners must create clear and unambiguous acceptance criteria for each Product Backlog item before it may be selected in Sprint Planning. | TRUE
3894 | How frequently the Product Owner should communicate and re-iterate his product vision to the Scrum Team and the Key Stakeholders? | Early and often
451 | What are the mandatory prerequisites to the Sprint Planning meeting? | There are no mandatory prerequisites.
3951 | Every Product Backlog Item should be created by the Product Owner personally and only then the Development Team can add details to it at the PO’s discretion. | TRUE
447 | Scrum mandates the use of burndown charts. | FALSE
2447 | My role as a Product Owner focuses on which two of the following? | Working with customers and stakeholder to identify the most important product requirements., Keeping the stakeholders informed of the project and release status.
466 | A baseline Product Backlog is called: | It is never baselined, it is a living artifact.
3939 | Who is responsible for the monitoring of the remaining work towards the Project Goal? | The Product Owner
3906 | What part of the capacity of the Development Team does Product Backlog refinement usually consume? | Not more than 10%
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | How readily his product can be absorbed and used by his customers, How much of the functionality of his product is being utilized, Direct customer feedback
2373 | Why would you expect a Product Owner to care about the Development Team adhering to its definition of "done"? Chosse two answers. | He doesn't have to care. Other systems aren't very good either., To have complete transparency into what has been done at the end of each Sprint.
505 | The backlog is ordered by: | The needs of the Product Owner
2061 | Which of the following best describes User Stories? | Support tools for analysis
532 | When maintaining the product backlog, this role represents the interests of the stakeholders, and ensures the value of the work completed: | Product Owner
2370 | Which two (2) metrics will help a Product Owner establish that value is being delivered? | Time to market, Customer satisfaction
390 | What two things best help the Product Owner manage the value of a product? | Validating assumptions of value through frequent releases., The order of the Product Backlog.
565 | The Developers should have a lead developer to ensure the work is properly executed. | FALSE
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
412 | The value delivered by a product can only be determined by revenue. | FALSE
3965 | What technique should be used for representing Product Backlog Items? | Any technique, even a mix of several techniques
3942 | Select the three best options to finish the sentence below. | compromises long-term quality of the Product, reflects some extra development work, is a real risk which can genuinely be incurred
Technical debt …
2423 | A Product Backlog is: (Choose 3 answers) | Managed by the Product Owner, Ordered based on priority, value, dependencies, and risk., An inventory of things to be done for the Product.
544 | While under development, the environment in which a product will be used changes and emerges. What is the effect on the Product Backlog? | It evolves to reflect what the product needs to be most valuable.
2425 | A new developer is having continuing conflicts with existing Development Team members and creating a hostile environment. If necessary, who is reponsible for removing the team member? | The Development Tem is responsible, and may need help from the Scrum Master.
446 | Who creates the Sprint Goal? | The Developers
2402 | A Product Owner with multiple teams working on one product should maintain separate Product Backlogs for each team. | FALSE
550 | Which two are properties of the Daily Scrum? (2 answers) | It is fifteen minutes or less in duration., Its location and time should remain constant.
2403 | A PO (Product Owner) is essentially the same thing as a traditional PM (Project Manager). | FALSE
3925 | Select the two meetings in which people outside the Scrum Team are allowed to participate. | The Sprint Planning, The Sprint Review
609 | Which is the most important stakeholder Product Owners must satisfy? | The product's users.
554 | Which objectives are covered as part of Sprint Planning? | Understanding what functionality the Product Owner desires within the next Sprint and figuring out how to do it.
553 | What is the major difference between Product Backlog and Sprint Backlog? | The Sprint Backlog is a subset of the Product Backlog.
2056 | What are the duties of a Product Owner on an Agile team? | Coordinate the team and make sure they are working on the features important to the customer
2059 | At a Sprint Review meeting (Demo), the Product Owner reviewed the working software and indicated that it does not fully meet what was required in the user story. Which of the statements below is not accurate? | This may have happened because acceptance criteria for this user story were not defined in sufficient detail to avoid ambiguity.
2434 | Who creates a P roduct Backlog item's estimate? | The Devlopment Team, alone.
499 | If multiple Teams are working on the same product, how should they write their definition of 'Done'? | There should be a single definition of Done for all Teams.
445 | On an Scrum team, the Scrum Master works to remove impediments from blocking the team's progress. This is known as what type of leadership? | Servant
457 | The Product Backlog should be transparent to the entire organization. | TRUE
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
3915 | Who is the leader in terms of getting feedback from the Key Stakeholders in the Sprint Review? | The Product Owner
594 | Acceptance criteria is a requirement for every Product Backlog item to be "Ready" for development. | TRUE
2418 | Sprint Reviews are an opportune time to collect customer feedback. | TRUE
2445 | Which Scrum values is affected by a lack of trust in the Scrum Team? | All of the answers
2416 | A Scrum Team has been working on a product for 9 sprints. A new Product Owner comes in, understanding he is accountable for Product Backlog. However, he is unsure about the purpose of the Product Backlog. He's read that the Product Backlog should be a list of all user fetures for the product. He goes to the Scrum Master asking where to put the other types of requirements acceptable on a Product Backlog? | Yes, they all belong on the Product Backlog. Product Backlog is supposed to be the 'single source of truth' for all the work for the product.
3934 | All the Scrum Teams working on the same product should have the same Sprint length. | FALSE
416 | Sprints are never longer than a calendar month. | TRUE
552 | The correct sequence of events in using Scrum framework is as follows: | Sprint Planning, Sprint, Daily Scrum, Sprint Review, and Sprint Retrospective.
563 | Who assigns ownership of the Sprint Backlog items during the Sprint? | There is no single owner of a Product Backlog item, the entire team owns the Sprint Backlog.
3904 | What happens when a Sprint is cancelled? Select three. | Any completed and “Done” Product Backlog items are reviewed, Several top Product Backlog Items are taken into the Sprint Backlog to replace the obsolete items, All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog
470 | There are 5 teams working on a product, how many Product Owners would there be? | 1
483 | A product increment should be released to production every Sprint | FALSE
603 | Which of the following is more important for leadership to provide when supporting their organization as they scale Scrum? | Values, principles, vision and the freedom to explore practices within the boundaries those values create.
2439 | Why is it important that there is only one Product Owner per product? Choose 3 answers. | It is clear who is accountable for the ultimate success of the product., It helps avoid barriers to effective communication and rapid decision-making., The Development Team always knows who determines priorities.
463 | A product owner and project manager are basically the same thing in Scrum. | FALSE
2407 | What activities would a Product Owner typically undertake in the phase between the end of the current Sprint and the start of the next Sprint? | There are no such activities. The next Sprint starts immediately after the current Sprint.
574 | How complete should the Sprint Backlog be at the end of the Sprint Planning meeting? | Enough to ensure there is work for the first few days of the Sprint.
2063 | A Product Owner asked the team to work over the week-end to deliver an additional feature not planned for the sprint, in order to produce a better product. What is the appropriate response from the Scrum Master? | The Scrum Master should suggest that the Product Owner waits until the next sprint or they stop the current sprint and re-prioritize the product backlog to reflect the requested change
403 | What two things should be done if the Product Owner is unavailable? | Within the Sprint, the Developers make the best decisions possible to assure progress toward the Sprint Goal, re-aligning with the Product Owner once he/she is available again., There should be a Product Owner team to allow a different person from that team to instantly take over the role of Product Owner.
386 | What variables should a Product Owner consider when ordering the Product Backlog? | Whatever is most appropriate for the Product Owner to achieve the product's goals and to optimize the value received
394 | Which description best fits the role of the Product Owner? | Value Maximizer
549 | Which of the following are true about the Product Owner role? (Select 3) | The Product Owner can be influenced by a committee., The Product Owner is one person., The Product Owner is accountable for ordering the Product Backlog.
3924 | How can the Product Owner bring his product vision to life (select 3)? | Articulating the product vision to the Scrum Team and the Key Stakeholders early and often, Via the Product Backlog and iterating towards that vision every Sprint, Utilizing the underlying empirical product planning features of Scrum
2458 | When does the second Sprint start? | Immediately after the first Sprint.
508 | Which item is NOT an attribute of the Product Backlog? | Owner
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
3889 | What is the recommended size of a Scrum Team? | 2021-11-03
3953 | What are the Scrum Artifacts? Select all applicable items. | Product Backlog, Increment, Sprint Backlog
430 | What happens if the customer no longer wants the feature that the Sprint Goal intended to meet? | The Product Owner should cancel the Sprint.
2442 | When many Development Teams are working on a single product, what best describes the definition of 'Done'? | All Development Teams must have a definition of 'Done' that makes their combined work potentialy releasable.
617 | When might a Sprint be abnormally terminated? | When the Sprint Goal becomes obsolete.
514 | The Product Owner is an optional attendee of the Sprint Retrospective. | FALSE
440 | The Project Manager plays the following role in Scrum: | There is no project manager role in Scrum.
2451 | The CEO asks the Development Team to add a "very important" item to a Sprint that is in progress. What should the Development Team do? | Inform the Product Owner so he/she can work with the CEO.
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | How readily his product can be absorbed and used by his customers, How much of the functionality of his product is being utilized, Direct customer feedback
2421 | The PO should have a complete and exhaustive Product Backlog before the first Sprint can start? | FALSE
526 | Stakeholders can interact with the Scrum team in which two ways? | Via interactions with the Product Owner., At the Sprint Review.
2376 | What might indicate to a Product Owner that she needs to work more with the Scrum Team? | The increment presented at the Sprint Review does not reflect what she thought she had asked for.
407 | The Sprint Review is the only time at which stakeholder feedback is taken into account. | FALSE
2437 | How should Product Backlog items be chosen when multiple Scrum Teams work from the same Product Backlog? | The Development Team pull in work in agreement with the Product Owner.
2393 | Which two of the following are true about the Scrum Master role? | The Scrum Master teaches the Development Team to keep the Scrum meetings to their timebox., The Scrum Master helps those outside the team interact with the Scrum Team.
3909 | Who is allowed to make changes in the Product Backlog? | The Product Owner, The Development Team, but with permission of the Product Owner
2069 | What is Velocity? | Velocity is a measure of a team's rate of progress per iteration
569 | In what ways does the Product Owner manage the value of the product? (Pick two) | Customer Feedback via Frequent Releases, Product Backlog Order
2367 | What are two responsibilities of testers in a Development Team? Choose 2 answers. | Everyone in the Development team is responsible for quality, Scrum has no "tester" role
607 | When can Developers cancel a Sprint? | It can't. Only Product Owners can cancel Sprints.
2383 | Who owns the Sprint Backlog? | The Development Team
3961 | Imagine the following situation. At the Sprint Retrospective meeting the Scrum Team identified some improvements that can be done. What should the Scrum Team do? Select the best option. | Make sure the Sprint Backlog for the next Sprint includes at least one high priority process improvement.
390 | What two things best help the Product Owner manage the value of a product? | Validating assumptions of value through frequent releases., The order of the Product Backlog.
3893 | Who decides whether to release the latest increment of the product? | The Product Owner
3902 | Where Scrum can be used? Check all the applicable items. | Managing the operation of an organization, Development of products and enhancements, Development of almost everything we use in our daily lives as individuals and societies, Development and sustaining of Cloud and other operational environments, Development of software and hardware, Research and identifying of viable markets, technologies, and product capabilities
2423 | A Product Backlog is: (Choose 3 answers) | Ordered based on priority, value, dependencies, and risk., An inventory of things to be done for the Product., Managed by the Product Owner
3894 | How frequently the Product Owner should communicate and re-iterate his product vision to the Scrum Team and the Key Stakeholders? | Early and often
3943 | What does the word “development” mean in the context of Scrum? Select the best option. | Complex work that can include all the suggested options and even more
2067 | Why are the top 20% of items of a Product Backlog the most important to accomplish? | Because according to the Pareto rule, 80 percentage of the value comes from 20 percentage of the work
2448 | What are three ways Scrum promotes self-organization? | By removing titles for Development Team members., By being a lightweight framework., By the Development Team decinding what work to do in a Sprint.
2385 | who can abnormally terminate a Sprint? | The Product Owner
2417 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Which two measures ensure that the Product Backlog is transparent? | The Product Backlog is ordered., The Product Backlog is available to all stakeholders.
2372 | If two Scrum Teams are added to the development of a product that previously had only one Scrum Team, what will be the immediate impact on the productivity of the original Scrum Team? | Its productivity is likely to decrease.
410 | It is mandatory for the Product Owner to monitor and share progress of Product Backlog through: | Any projective practice based on trends of work completed and upcoming work.
555 | The Product Owner can delegate the ordering of the Product Backlog. | FALSE
487 | A 4-hour Sprint Planning meeting is typical for a Sprint or Iteration that is how long? | Two weeks
3948 | Product Backlog Refinement practice focuses on Items for upcoming Sprints, not the current Sprint in progress. True or false? | TRUE
442 | Who must do all of the work to ensure the Product Backlog items conform to the definition of “Done”? | The Scrum Team
2396 | For the purpose of transparency, when does Scrum say a new increment of working software must be available? | At the end of every Sprint.
574 | How complete should the Sprint Backlog be at the end of the Sprint Planning meeting? | Enough to ensure there is work for the first few days of the Sprint.
2438 | Who should know the most about the progress toward a business objective or a release? | The Product Owner
535 | The Product Owner determines how many Product Backlog items the Developers select for a Sprint. | False.
559 | Which three of the following points about the daily Scrum are TRUE? | It is time-boxed., It is held at the same place and time every day., The Scrum Master enforces the rule that only Development Team members participate.
482 | All of the following are true about change during a Sprint EXCEPT: | Changes can be made that impact the Sprint goal.
558 | Scrum is a container for other techniques and methodologies. | TRUE
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
2389 | The "cone of uncertainty" can be used to do what? | Illustrate that, as a forecast lengthens, it is increasingly less certain.
2366 | Which of these may a Development Team deliver at the end of a Sprint? | An increment of working software that is "done".
3925 | Select the two meetings in which people outside the Scrum Team are allowed to participate. | The Sprint Planning, The Sprint Review
412 | The value delivered by a product can only be determined by revenue. | FALSE
542 | Which technique is the LEAST productive way for the Scrum Master to ensure that the Developers communicates effectively with the Product Owner? | Act as a go-between for them.
549 | Which of the following are true about the Product Owner role? (Select 3) | The Product Owner is accountable for ordering the Product Backlog., The Product Owner can be influenced by a committee., The Product Owner is one person.
2394 | In the middle of the Sprint, the customer decides that there are 2 new features she wants. The Product Owner could: | Add it to the Product Backlog., Ask the Development Team to consider whether they can add thses features to the current Sprint.
2431 | To get started in terms of what to build, Scrum requires no more than a Product Owner with enough ideas for a first Sprint, a Development Team to implement those ideas and a Scrum Master to help guide the process. | TRUE
509 | Organizational value is captured through which three evidence-based metrics? | Time to market, Ability to innovate, Current Value
2414 | What is typical work for a Product Owner in a Sprint? Choose 2 answers. | Work with the Development Team on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The ScrumMaster
3917 | How does Definition of “Done” help to the Scrum Team? Select the three most applicable items. | DoD ensures artifact transparency, Guides the Development Team in knowing how many Product Backlog items it can select during a Sprint Planning, DoD is used to assess when work is complete on the product Increment
473 | Backlog Grooming and Backlog Refinement are the same thing. | TRUE
2459 | Which statement best describes the Sprint Backlog as outcome of the Sprint Planning? | It is the Development Team's plan for the Sprint.
462 | A new Sprint starts immediately following the previous Sprint. | TRUE
470 | There are 5 teams working on a product, how many Product Owners would there be? | 1
471 | If the Product Backlog is not ready for Sprint Planning, what happens? | Cancel the sprint until backlog is ready.
565 | The Developers should have a lead developer to ensure the work is properly executed. | FALSE
557 | When does backlog refinement occur? | During the Sprint, in preparation for the next Sprint(s).
545 | Which of the following is an example of an increment of working software? | Additional features in a useable state that complement those delivered in previous iterations.
3938 | Who is responsible for creation of the Definition of “Done”? | The Development Team
2386 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Select two ways to maintain the Product Backlog to maximize its transparency? Choose 2 answers. | Product Backlog items are sized appropriately, i.e. not bigger than a Sprint and with a preference for several do-able items in a Sprint., The Product Backlog always has the most actual insights.
3922 | Could the Product Owner and the Scrum Master be a part of the Development Team? | TRUE
3907 | The Product Owner wants to apply some non-functional requirements to the Product. What is the best way to proceed? | Add the non-functional requirements to the DoD and check every Increment against these criteria
2452 | When should a Sprint Goal be created? | During Sprint Planning.
3901 | When the Scrum Team is allowed to interact with the Key Stakeholders (select the most applicable option)? | Any time where it’s valuable to have the Stakeholder input
431 | Who is NOT part of the Scrum Team (Choose 2)? | Customer, The Development Team
609 | Which is the most important stakeholder Product Owners must satisfy? | The product's users.
3932 | What does Burn-down Chart show? | How much work remains till the end of the Sprint
2365 | How should a Development Team deal with non-functional requirements?
3924 | How can the Product Owner bring his product vision to life (select 3)? | Articulating the product vision to the Scrum Team and the Key Stakeholders early and often, Via the Product Backlog and iterating towards that vision every Sprint, Utilizing the underlying empirical product planning features of Scrum
2458 | When does the second Sprint start? | Immediately after the first Sprint.
508 | Which item is NOT an attribute of the Product Backlog? | Owner
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
3889 | What is the recommended size of a Scrum Team? | 2021-11-03
3953 | What are the Scrum Artifacts? Select all applicable items. | Product Backlog, Increment, Sprint Backlog
430 | What happens if the customer no longer wants the feature that the Sprint Goal intended to meet? | The Product Owner should cancel the Sprint.
2442 | When many Development Teams are working on a single product, what best describes the definition of 'Done'? | All Development Teams must have a definition of 'Done' that makes their combined work potentialy releasable.
617 | When might a Sprint be abnormally terminated? | When the Sprint Goal becomes obsolete.
514 | The Product Owner is an optional attendee of the Sprint Retrospective. | TRUE
440 | The Project Manager plays the following role in Scrum: | There is no project manager role in Scrum.
2451 | The CEO asks the Development Team to add a "very important" item to a Sprint that is in progress. What should the Development Team do? | Inform the Product Owner so he/she can work with the CEO.
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | How readily his product can be absorbed and used by his customers, How much of the functionality of his product is being utilized, Direct customer feedback
2421 | The PO should have a complete and exhaustive Product Backlog before the first Sprint can start? | FALSE
526 | Stakeholders can interact with the Scrum team in which two ways? | Via interactions with the Product Owner., At the Sprint Review.
2376 | What might indicate to a Product Owner that she needs to work more with the Scrum Team? | The increment presented at the Sprint Review does not reflect what she thought she had asked for.
407 | The Sprint Review is the only time at which stakeholder feedback is taken into account. | FALSE
2437 | How should Product Backlog items be chosen when multiple Scrum Teams work from the same Product Backlog? | The Development Team pull in work in agreement with the Product Owner.
2393 | Which two of the following are true about the Scrum Master role? | The Scrum Master teaches the Development Team to keep the Scrum meetings to their timebox., The Scrum Master helps those outside the team interact with the Scrum Team.
3909 | Who is allowed to make changes in the Product Backlog? | The Product Owner, The Development Team, but with permission of the Product Owner
2069 | What is Velocity? | Velocity is a measure of a team's rate of progress per iteration
569 | In what ways does the Product Owner manage the value of the product? (Pick two) | Customer Feedback via Frequent Releases, Product Backlog Order
2367 | What are two responsibilities of testers in a Development Team? Choose 2 answers. | Everyone in the Development team is responsible for quality, Scrum has no "tester" role
607 | When can Developers cancel a Sprint? | It can't. Only Product Owners can cancel Sprints.
2383 | Who owns the Sprint Backlog? | The Development Team
3961 | Imagine the following situation. At the Sprint Retrospective meeting the Scrum Team identified some improvements that can be done. What should the Scrum Team do? Select the best option. | Make sure the Sprint Backlog for the next Sprint includes at least one high priority process improvement.
390 | What two things best help the Product Owner manage the value of a product? | Validating assumptions of value through frequent releases., The order of the Product Backlog.
3893 | Who decides whether to release the latest increment of the product? | The Product Owner
3902 | Where Scrum can be used? Check all the applicable items. | Managing the operation of an organization, Development of products and enhancements, Development of almost everything we use in our daily lives as individuals and societies, Development and sustaining of Cloud and other operational environments, Development of software and hardware, Research and identifying of viable markets, technologies, and product capabilities
2423 | A Product Backlog is: (Choose 3 answers) | Ordered based on priority, value, dependencies, and risk., An inventory of things to be done for the Product., Managed by the Product Owner
3894 | How frequently the Product Owner should communicate and re-iterate his product vision to the Scrum Team and the Key Stakeholders? | Early and often
3943 | What does the word “development” mean in the context of Scrum? Select the best option. | Complex work that can include all the suggested options and even more
2067 | Why are the top 20% of items of a Product Backlog the most important to accomplish? | Because according to the Pareto rule, 80 percentage of the value comes from 20 percentage of the work
2448 | What are three ways Scrum promotes self-organization? | By removing titles for Development Team members., By being a lightweight framework., By preventing stakeholders from entering the development room.
2385 | who can abnormally terminate a Sprint? | The Product Owner
2417 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Which two measures ensure that the Product Backlog is transparent? | The Product Backlog is ordered., The Product Backlog is available to all stakeholders.
2372 | If two Scrum Teams are added to the development of a product that previously had only one Scrum Team, what will be the immediate impact on the productivity of the original Scrum Team? | Its productivity is likely to decrease.
410 | It is mandatory for the Product Owner to monitor and share progress of Product Backlog through: | Any projective practice based on trends of work completed and upcoming work.
555 | The Product Owner can delegate the ordering of the Product Backlog. | FALSE
487 | A 4-hour Sprint Planning meeting is typical for a Sprint or Iteration that is how long? | Two weeks
3948 | Product Backlog Refinement practice focuses on Items for upcoming Sprints, not the current Sprint in progress. True or false? | TRUE
442 | Who must do all of the work to ensure the Product Backlog items conform to the definition of “Done”? | The Developers
2396 | For the purpose of transparency, when does Scrum say a new increment of working software must be available? | At the end of every Sprint.
574 | How complete should the Sprint Backlog be at the end of the Sprint Planning meeting? | Enough to ensure there is work for the first few days of the Sprint.
2438 | Who should know the most about the progress toward a business objective or a release? | The Product Owner
535 | The Product Owner determines how many Product Backlog items the Developers select for a Sprint. | False.
559 | Which three of the following points about the daily Scrum are TRUE? | It is time-boxed., It is held at the same place and time every day., The Scrum Master enforces the rule that only Development Team members participate.
482 | All of the following are true about change during a Sprint EXCEPT: | Change may occur as scope is clarified between the Product Owner and the Developers.
558 | Scrum is a container for other techniques and methodologies. | TRUE
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
2389 | The "cone of uncertainty" can be used to do what? | Illustrate that, as a forecast lengthens, it is increasingly less certain.
2366 | Which of these may a Development Team deliver at the end of a Sprint? | An increment of working software that is "done".
3925 | Select the two meetings in which people outside the Scrum Team are allowed to participate. | The Sprint Planning, The Sprint Review
412 | The value delivered by a product can only be determined by revenue. | FALSE
542 | Which technique is the LEAST productive way for the Scrum Master to ensure that the Developers communicates effectively with the Product Owner? | Act as a go-between for them.
549 | Which of the following are true about the Product Owner role? (Select 3) | The Product Owner is accountable for ordering the Product Backlog., The Product Owner can be influenced by a committee., The Product Owner is one person.
2394 | In the middle of the Sprint, the customer decides that there are 2 new features she wants. The Product Owner could: | Add it to the Product Backlog., Ask the Development Team to consider whether they can add thses features to the current Sprint.
2431 | To get started in terms of what to build, Scrum requires no more than a Product Owner with enough ideas for a first Sprint, a Development Team to implement those ideas and a Scrum Master to help guide the process. | TRUE
509 | Organizational value is captured through which three evidence-based metrics? | Time to market, Ability to innovate, Current Value
2414 | What is typical work for a Product Owner in a Sprint? Choose 2 answers. | Work with the Development Team on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The ScrumMaster
3917 | How does Definition of “Done” help to the Scrum Team? Select the three most applicable items. | DoD ensures artifact transparency, Guides the Development Team in knowing how many Product Backlog items it can select during a Sprint Planning, DoD is used to assess when work is complete on the product Increment
473 | Backlog Grooming and Backlog Refinement are the same thing. | TRUE
2459 | Which statement best describes the Sprint Backlog as outcome of the Sprint Planning? | It is a complete list of all work to be done in a Sprint.
462 | A new Sprint starts immediately following the previous Sprint. | TRUE
470 | There are 5 teams working on a product, how many Product Owners would there be? | 1
471 | If the Product Backlog is not ready for Sprint Planning, what happens? | Cancel the sprint until backlog is ready.
565 | The Developers should have a lead developer to ensure the work is properly executed. | FALSE
557 | When does backlog refinement occur? | During the Sprint, in preparation for the next Sprint(s).
545 | Which of the following is an example of an increment of working software? | Additional features in a useable state that complement those delivered in previous iterations.
3938 | Who is responsible for creation of the Definition of “Done”? | The Development Team
2386 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Select two ways to maintain the Product Backlog to maximize its transparency? Choose 2 answers. | Product Backlog items are sized appropriately, i.e. not bigger than a Sprint and with a preference for several do-able items in a Sprint., The Product Backlog always has the most actual insights.
3922 | Could the Product Owner and the Scrum Master be a part of the Development Team? | TRUE
3907 | The Product Owner wants to apply some non-functional requirements to the Product. What is the best way to proceed? | Create a new Item for every requirement in the Product Backlog
2452 | When should a Sprint Goal be created? | During Sprint Planning.
3901 | When the Scrum Team is allowed to interact with the Key Stakeholders (select the most applicable option)? | The Sprint Review
431 | Who is NOT part of the Scrum Team (Choose 2)? | Customer, The Development Team
609 | Which is the most important stakeholder Product Owners must satisfy? | The product's users.
3932 | What does Burn-down Chart show? | How much work remains till the end of the Sprint
2365 | How should a Development Team deal with non-functional requirements? | Ensure every Increment meets them.
562 | When is a Product Backlog item 'Ready' for the Sprint? | It can be Done in one Sprint.
3943 | What does the word “development” mean in the context of Scrum? Select the best option. | Complex work that can include all the suggested options and even more
613 | How often should customer satisfaction be measured? | Frequently.
420 | What are two ways in which the Product Owner manages Inspection of the Increment? | By inviting stakeholders to give feedback in the Sprint Review., By presenting the status of the Product Backlog at the Sprint Review.
2439 | Why is it important that there is only one Product Owner per product? Choose 3 answers. | The Development Team always knows who determines priorities., It is clear who is accountable for the ultimate success of the product., It helps avoid barriers to effective communication and rapid decision-making.
484 | Non-functional requirements (NFRs) must be captured in the Definition of Done. | FALSE
2441 | Multiple Scrum Team working on the same product or system all select work from the same Product Backlog. | TRUE
3919 | Which Key Value Areas (KVA) categories should the Product Owner consider to measure and track the creation and delivery of value to the market place (select three)? | Current Value, Time-to-Market, Ability to Innovate
3892 | What two attributes are optional for a Product Backlog Item? | Dependencies, Test descriptions that will prove PB Item completeness when "Done"
2437 | How should Product Backlog items be chosen when multiple Scrum Teams work from the same Product Backlog? | The Development Team pull in work in agreement with the Product Owner.
408 | What best describes the relationship of the Product Owner and the stakeholders? | The Product Owner actively asks for stakeholder input and expectations to process into the Product Backlog.
3952 | Who has the “last say” on the order of items in the Product Backlog? | The Product Owner
3944 | Select the five Scrum Values. | Openness, Focus, Commitment, Courage, Respect
564 | Pick the roles that support the Scrum Master in removing impediments. (Choose two) | The Developers, Senior Management
2453 | What are criteria to order Product Backlog items? | All of the answers.
2371 | Which two things should the Development Team do during the first Sprint? | Develop at least one piece of functionality., Create an Increment of potentially releasable software.
2435 | A product's success is measured by: | The impact on revenue., The impact on customer satisfaction., The impact on cost.
3898 | The Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment. | TRUE
589 | Scrum does not scale to large teams. | FALSE
387 | What preconditions must be fulfilled in order to allow Sprint Planning to begin? | There are no such preconditions
510 | The Product Owner actively asks for stakeholder input into the Product Backlog. | TRUE
2429 | Who is responsible for engaging the stakeholders? | The Product Owner.
406 | A Product Owner is entitled to postpone the start of a new Sprint after the conclusion of a previous Sprint for the following reason: | There is no acceptable reason. A new Sprint starts immediately after the conclusion of the previous Sprint.
2396 | For the purpose of transparency, when does Scrum say a new increment of working software must be available? | At the end of every Sprint.
3934 | All the Scrum Teams working on the same product should have the same Sprint length. | FALSE
3908 | What is the Sprint Backlog? | The Product Backlog items selected for this Sprint
2374 | Which Scrum Values are exhibited by not building Product Backlog items that have low business value? | Economic Value Added, Earned Value
2392 | Which output from Sprint Planning provides the Development Team with a target and overarching direction for the Sprint? | The Sprint Goal
2393 | Which two of the following are true about the Scrum Master role? | The Scrum Master teaches the Development Team to keep the Scrum meetings to their timebox., The Scrum Master helps those outside the team interact with the Scrum Team.
3951 | Every Product Backlog Item should be created by the Product Owner personally and only then the Development Team can add details to it at the PO’s discretion. | TRUE
608 | How much time is required after a Sprint to prepare for the next Sprint? | None. A new Sprint starts immediately following the end of the previous Sprint.
442 | Who must do all of the work to ensure the Product Backlog items conform to the definition of “Done”? | The Developers
466 | A baseline Product Backlog is called: | It is never baselined, it is a living artifact.
2381 | A Scrum team is only allowed to meet with stakeholders during Sprint Review. | FALSE
3911 | Who is responsible for all estimates in the Product Backlog? | The Development Team
3909 | Who is allowed to make changes in the Product Backlog? | The Development Team, but with permission of the Product Owner, The Product Owner
2378 | All work to be done by the Development Team must ultimately originate from the Product Backlog? | TRUE
3945 | What is the essence of Scrum? Select the most appropriate option. | A small team of people that is highly flexible and adaptive
2061 | Which of the following best describes User Stories? | Support tools for analysis
2055 | What is the primary measure of progress in Agile? | Working software is the primary measure of progress
483 | A product increment should be released to production every Sprint | FALSE
494 | The Product Backlog is baselined at the start of the project and not changed for at least three Sprints. | FALSE
499 | If multiple Teams are working on the same product, how should they write their definition of 'Done'? | There should be a single definition of Done for all Teams.
2430 | A product's success is measured by: | The impact on cost., The impact of customer satisfaction., The impact on revenue.
475 | Sprint burndown charts are an efficient tracking tool because they show: | An estimate of the total work remaining for the Sprint.
445 | On an Scrum team, the Scrum Master works to remove impediments from blocking the team's progress. This is known as what type of leadership? | Servant
3947 | Who is allowed to change the Sprint Backlog during the Sprint? | The Development Team
501 | The Product Owner must provide transparency to the status of the Product Backlog using a: | Any means necessary to reflect work finished and work remaining.
3950 | Who is the chief product visionary? | The Product Owner
529 | Pick which 3 activities are the responsibility of the Scrum Master in Scrum. | Facilitate meetings, Remove impediments, Champion Scrum
461 | Which is a report of all the work that is 'Done?' | Burndown chart
2415 | What typically happens if the Product Backlog is not sufficiently clear at Sprint Planning? | The Development Team has difficulties creating a forecast of work for the Sprint.
2455 | Which are two properties of the Daily Scrum? | It is fifteen minutes or less in duration., Its location and time should remain constant.
463 | A product owner and project manager are basically the same thing in Scrum. | FALSE
3938 | Who is responsible for creation of the Definition of “Done”? | The Development Team
574 | How complete should the Sprint Backlog be at the end of the Sprint Planning meeting? | Enough to ensure there is work for the first few days of the Sprint.
2365 | How should a Development Team deal with non-functional requirements? | Ensure every Increment meets them.
3954 | Product Backlog Refinement … | Is an ongoing process, Is the act of adding detail, estimates, and order to Product Backlog items, Takes no more than 10% of the capacity of the Development Team
Select the three most applicable sentence endings.
3966 | Who is allowed to tell the Development Team to work from a set of requirements? | The Product Owner
551 | What happens when the Sprint is cancelled? | The completed Sprint Backlog items are evaluated for a release and incomplete items are put back to the Product Backlog.
2452 | When should a Sprint Goal be created? | During Sprint Planning.
3923 | Select the two focus areas that are not considered in executing Value Driven Development by the Product Owner. | Remover of impediments to the Development Team’s progress, Coach of the Development Team in self-organization and cross-functionality
558 | Scrum is a container for other techniques and methodologies. | TRUE
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | How much of the functionality of his product is being utilized, Direct customer feedback, Minimizing changes to project scope
398 | The Developers find out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? | Rework the selected Product Backlog items with the Developers to meet the Sprint Goal.
3921 | How long does the Product Backlog exists? | While the Product exists
2370 | Which two (2) metrics will help a Product Owner establish that value is being delivered? | Time to market, Customer satisfaction
459 | Which of the following three statements are true about the Product Owner role? | The Product Owner can be influenced by a committee., The Product Owner is one person., The Product Owner is accountable for ordering the Product Backlog.
414 | How can a Product Owner use time-boxed Sprints to obtain feedback from users and the market? | Through frequent delivery of Increments of the product into the market.
455 | Who is responsible for maximizing the value of the product? | The Product Owner
3927 | What are Product Backlog features? Select three. | As long as a product exists, its Product Backlog also exists, It is never complete, It is dynamic
458 | The optimum size of the Scrum Team is: | Less than 10 people
3948 | Product Backlog Refinement practice focuses on Items for upcoming Sprints, not the current Sprint in progress. True or false? | TRUE
550 | Which two are properties of the Daily Scrum? (2 answers) | Its location and time should remain constant., It is fifteen minutes or less in duration.
599 | The total cost of ownership (TCO) for a product is the sum of all investments required to design, develop, run and support the product. | TRUE
2433 | In order to maximize the value of the product, a Product Owner needs awareness of the following: | All of the answers
2394 | In the middle of the Sprint, the customer decides that there are 2 new features she wants. The Product Owner could: | Ask the Development Team to consider whether they can add thses features to the current Sprint., Add it to the Product Backlog.
505 | The backlog is ordered by: | The needs of the Product Owner
2069 | What is Velocity? | Velocity is a measure of a team's rate of progress per iteration
504 | In the Sprint Review, the Product Backlog is re-prioritized by the stakeholders. | FALSE
387 | What preconditions must be fulfilled in order to allow Sprint Planning to begin? | There are no such preconditions
2446 | How is management external to the Scrum Team involved in the Daily Scrum? | The Development Team self-manages and is the only management required at the Daily Scrum.
3940 | What is the Increment? | The sum of all the Product Backlog items completed during the Sprint and the value of the increments of all previous Sprints
416 | Sprints are never longer than a calendar month. | TRUE
612 | Who is responsible for clearly expressing Product Backlog Items? | The Product Owner.
2386 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Select two ways to maintain the Product Backlog to maximize its transparency? Choose 2 answers. | The Product Backlog always has the most actual insights., Product Backlog items are sized appropriately, i.e. not bigger than a Sprint and with a preference for several do-able items in a Sprint.
2414 | What is typical work for a Product Owner in a Sprint? Choose 2 answers. | Work with the Development Team on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
412 | The value delivered by a product can only be determined by revenue. | FALSE
2380 | How small should a 'ready' Product Backlog item be? | Small enough to build in 1 Sprint.
546 | Which of the following two items are not topics of discussion within a Sprint Retrospective? | Functionality implemented as a result of the Sprint., Sprint Backlog for the next Sprint.
2442 | When many Development Teams are working on a single product, what best describes the definition of 'Done'? | All Development Teams must have a definition of 'Done' that makes their combined work potentialy releasable.
3895 | It is a good practice to have at least two Product Owners on big projects. | FALSE
2385 | who can abnormally terminate a Sprint? | The Product Owner
498 | What does the 'cone of uncertainty' tell us about a Scrum project? | We have the most uncertainty about a project's lenght during the first couple of sprints.
2398 | Why is the Daily Scrum held at the same time and the same place? | The consistency reduces complexity.
485 | The Product Owner needs to be aware of which three things to effectively maximize the value of the product? | Customer Feedback, Product Vision, Team Velocity
2384 | Who is responsible for tracking the remaining work of the Sprint? | The Development Team
3964 | Who participates in the Sprint Planning? Select three. | The Development Team, The Key Stakeholders, The Product Owner
2388 | As a Product Owner, if you had access to the following individuals, what sources might you consult with when considering the value of a product? Choose all that apply. | Sales Executive or Sales Leader, Customers and Prospects, Development Team, CEO, Market research results and analyst reports
2439 | Why is it important that there is only one Product Owner per product? Choose 3 answers. | The Development Team always knows who determines priorities., It is clear who is accountable for the ultimate success of the product., It helps avoid barriers to effective communication and rapid decision-making.
2401 | Which three of the following are timeboxed events in Scrum? | Sprint Planning, Sprint Retrospective, Daily Scrum
2056 | What are the duties of a Product Owner on an Agile team? | Coordinate the team and make sure they are working on the features important to the customer
548 | What are some consequences if a Development does not have a consistent definition of done from Sprint to Sprint? | All of the answers.
3925 | Select the two meetings in which people outside the Scrum Team are allowed to participate. | The Sprint Planning, The Sprint Review
3909 | Who is allowed to make changes in the Product Backlog? | The Development Team, but with permission of the Product Owner, The Product Owner
2434 | Who creates a P roduct Backlog item's estimate? | The Development Team after clarifying requirements with the Product Owner.
444 | Why does Developers need a Sprint Goal? | The Developers are more focused with a specific goal.
402 | What is the Product Owner accountable for in Scrum? | Creating and sustaining a Product Backlog that maximizes value and represents the needs of the stakeholders.
441 | In Scrum, who is responsible for managing the team? | Scrum Master
413 | How does an organization know that a product built through Scrum is successful? | By releasing often, and updating key performance indicators (KPIs) on value after every release and feeding this information back into work on the Product Backlog.
399 | Who creates the definition of 'Done'? | The development organization (or Developers if none is available from the development organization).
499 | If multiple Teams are working on the same product, how should they write their definition of 'Done'? | There should be a single definition of Done for all Teams.
2383 | Who owns the Sprint Backlog? | The Development Team
3960 | All Development Teams working on the same Product should use the same Product Backlog. | TRUE
2068 | The term "pigs" is used to refer to which of the following roles in a Scrum project? | The team
2367 | What are two responsibilities of testers in a Development Team? Choose 2 answers. | Scrum has no "tester" role, Everyone in the Development team is responsible for quality
2067 | Why are the top 20% of items of a Product Backlog the most important to accomplish? | Because according to the Pareto rule, 80 percentage of the value comes from 20 percentage of the work
3896 | In which meetings the Key Stakeholders are allowed to participate? | The Sprint Planning
536 | Please select which statement is the MOST accurate: | Refinement is a part-time activity during a Sprint between the Product Owner and the Scrum Master.
3933 | Who identifies the Key Stakeholders for the Product? | The Product Owner
2424 | Product Owners must specify complete acceptance criteria for a Product Backlog item before the team can select the item in Sprint Planning. | FALSE
398 | The Developers find out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? | Cancel the Sprint.
472 | On Agile teams, conflict is to be avoided at all cost. | FALSE
468 | Scrum is both an iterative and incremental Agile process. | TRUE
531 | Pick 5 activities that are the responsibility of the Developers in Scrum. | Designs software, Provides estimates, Volunteers for tasks, Prioritizes the backlog, Forecasts delivery of PBIs, Makes technical decisions
2456 | Which topics should be discussed in the Sprint Review? | All of the answers.
3929 | What factors should be considered by the Product Owner in the release decision (select four)? | Approval of the Key Stakeholders, Can customers actually absorb the new release?, Does the Increment meet the Definition of “Done”?, The amount of work remaining toward the Sprint Goal
503 | When was Scrum first introduced? | In 1995 at a conference presentation.
2445 | Which Scrum values is affected by a lack of trust in the Scrum Team? | All of the answers
3936 | The Product Owner should be expertly aware of the marketplace for the product. | TRUE
400 | To what extent does technical debt limit the value a Product Owner can get from a product? Select two answers. | The velocity at which new functionality can be created is reduced when you have technical debt., Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product.
2054 | The product owner has removed features from the release. How will this be represented in the release burndown bar chart? | Bottom of the bar is lowered
2061 | Which of the following best describes User Stories? | Support tools for analysis
2411 | What is the role of the Product Owner in crafting the Sprint Goal? | The PO has no role in it. This is the Development Team's responsibility.
614 | The Product Owner is accountable for the functionality included in each Increment. Does he or she have the final say over the definition of "Done"? | No, the Development Team is responsible for the definition of "Done". The Product Owner may be consulted.
447 | Scrum mandates the use of burndown charts. | FALSE
561 | What is the primary purpose of the Sprint Review? | Review the output of the Sprint and decide what to do next.
511 | When is the Sprint Backlog finalized? | During the Sprint
466 | A baseline Product Backlog is called: | It is never baselined, it is a living artifact.
3942 | Select the three best options to finish the sentence below. | belongs entirely to the Development Team. No one else should know about it., reflects some extra development work, compromises long-term quality of the Product
Technical debt …
3889 | What is the recommended size of a Scrum Team? | 2021-11-03
2069 | What is Velocity? | Velocity is a measure of a team's rate of progress per iteration
422 | Incremental delivery means: | Release working software only after testing each increment.
2406 | A Product Owner can measure success by an increase in the team's velocity. | FALSE
419 | A servant leadership role includes: | Shielding team members from interruptions.
2389 | The "cone of uncertainty" can be used to do what? | Project what will be complete by a given Sprint.
2379 | What is Product Owner work that a Product Owner might delegate? | Writing User Stories
3903 | Who is responsible for promoting and supporting Scrum? Select the best choice. | The Scrum Master
2462 | At the end of a Sprint a Product Backlog item worked on during the Sprint does not meet the definition of done. What two things should happen with the undone Product Backlog item? | Put it on the Product Backlog for the Product Owner to decide what to do with it., Do not include the item in the increment this Sprint.
533 | Which of the following is NOT part of the Scrum Framework? | Characteristics
2366 | Which of these may a Development Team deliver at the end of a Sprint? | An increment of working software that is "done".
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
2405 | There are multiple teams working on one product. Each team should have a separate Product Owner. | FALSE
526 | Stakeholders can interact with the Scrum team in which two ways? | At the Sprint Review., Via interactions with the Product Owner.
544 | While under development, the environment in which a product will be used changes and emerges. What is the effect on the Product Backlog? | It evolves to reflect what the product needs to be most valuable.
507 | The Product Owner should be with the Developers full time. | FALSE
596 | Typically calculated is Story Points, this is the rate at which the team converts items to "Done" in a single Sprint: | Velocity
449 | If the Sprint Backlog cannot be completed in a Sprint, who resolves the issue? | Both the Product Owner and Developers
3908 | What is the Sprint Backlog? | The Product Backlog items selected for this Sprint
3955 | Who should do the legwork of gathering the marketplace data for the Product Owner? | It does not matter who does the legwork
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
550 | Which two are properties of the Daily Scrum? (2 answers) | Its location and time should remain constant., It is fifteen minutes or less in duration.
2063 | A Product Owner asked the team to work over the week-end to deliver an additional feature not planned for the sprint, in order to produce a better product. What is the appropriate response from the Scrum Master? | The Scrum Master should suggest that the Product Owner waits until the next sprint or they stop the current sprint and re-prioritize the product backlog to reflect the requested change
3911 | Who is responsible for all estimates in the Product Backlog? | The Product Owner
454 | Who is responsible for maximizing the value of the product backlog? | The Product Owner.
498 | What does the 'cone of uncertainty' tell us about a Scrum project? | We have the most uncertainty about a project's lenght during the first couple of sprints.
2387 | The Product Owner must release each Increment to production. | When it makes sense.
3904 | What happens when a Sprint is cancelled? Select three. | All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog, Several top Product Backlog Items are taken into the Sprint Backlog to replace the obsolete items, Any completed and “Done” Product Backlog items are reviewed
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The ScrumMaster
467 | An important customer wants a new feature as soon as possible, what should the Product Owner do? | Add the features to the next Sprint Planning meeting.
3951 | Every Product Backlog Item should be created by the Product Owner personally and only then the Development Team can add details to it at the PO’s discretion. | TRUE
2457 | When shoud the Product Backlog be refined? Choose 2 answers. | The PO and the Development Team do it in the actual Sprint if they haven't been able to do it in preceding Sprints., The PO and the Development Team do it in the 1-2 preceding Sprints.
569 | In what ways does the Product Owner manage the value of the product? (Pick two) | Product Backlog Order, Customer Feedback via Frequent Releases
527 | High-performing teams feature which of the following sets of characteristics? | Consensus-driven, empowered, plan-driven.
544 | While under development, the environment in which a product will be used changes and emerges. What is the effect on the Product Backlog? | It evolves to reflect what the product needs to be most valuable.
446 | Who creates the Sprint Goal? | The Developers
2373 | Why would you expect a Product Owner to care about the Development Team adhering to its definition of "done"? Chosse two answers. | To have complete transparency into what has been done at the end of each Sprint., To influence the Total Cost of Ownership of the product.
472 | On Agile teams, conflict is to be avoided at all cost. | FALSE
475 | Sprint burndown charts are an efficient tracking tool because they show: | An estimate of the total work remaining for the Sprint.
3949 | What does Product Backlog management include? Select three most applicable items. | Ordering the items in the Product Backlog to best achieve goals and missions, Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next, Moving Product Backlog items into the Sprint Backlog
2365 | How should a Development Team deal with non-functional requirements? | Ensure every Increment meets them.
600 | How can the Product Owner impact technical debt? | Ask the team to improve the Definition of Done.
409 | The Product Owner manages the Product Backlog. Who is accountable for estimating the effort to complete the Product Backlog items? | The Product Owner. The Product Owner is required to commit on delivery to the users and the stakeholders.
481 | No one, not even the Product Owner, tells the Developers how to build the product. | TRUE
3928 | Who is responsible for tracking the total work remaining in the Sprint Backlog to project the likelihood of achieving the Sprint Goal? | The Development Team
559 | Which three of the following points about the daily Scrum are TRUE? | It is time-boxed., The Scrum Master enforces the rule that only Development Team members participate., It is held at the same place and time every day.
2438 | Who should know the most about the progress toward a business objective or a release? | The Product Owner
2444 | You are a product manager with a proven track in your company. Your management has asked you to take the lead in the development of a new product. Six teams new to Scrum will build this product. What would you strive for? Select two. | The product has one Product Backlog., There should be only one Product Owner.
3953 | What are the Scrum Artifacts? Select all applicable items. | Product Backlog, Increment, Sprint Backlog
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
452 | How do you ensure that performance requirements are addressed by the Developers? (pick 2) | Add these requirements to the Definition of Done., Add Product Backlog items to address performance.
3955 | Who should do the legwork of gathering the marketplace data for the Product Owner? | It does not matter who does the legwork
2385 | who can abnormally terminate a Sprint? | The Product Owner
2419 | The Product Backlog is ordered by: | Importance, where the most important items are at the top of all items.
3931 | When something about Scrum frustrates the Product Owner, the PO can delegate some responsibilities to the Scrum Master. | FALSE
500 | If there are multiple Scrum teams working on a product, each needs its own definition of 'Done'. | FALSE
2430 | A product's success is measured by: | The impact of customer satisfaction., The impact on revenue., The impact on cost.
3894 | How frequently the Product Owner should communicate and re-iterate his product vision to the Scrum Team and the Key Stakeholders? | Early and often
2447 | My role as a Product Owner focuses on which two of the following? | Keeping the stakeholders informed of the project and release status., Working with customers and stakeholder to identify the most important product requirements.
2065 | Which of the following best describes tools product owners can use to better perform their role, enhance collaboration in teams, and are especially effective when crafting a product vision and direction that hits the mark? | Innovation games
596 | Typically calculated is Story Points, this is the rate at which the team converts items to "Done" in a single Sprint: | Velocity
2401 | Which three of the following are timeboxed events in Scrum? | Daily Scrum, Sprint Retrospective, Sprint Planning
489 | To truly adopt Scrum, you must pick and choose which roles, artifacts, events, and rules are right for your organization. | FALSE
3905 | Who is allowed to participate in the Daily Scrum? | The Development Team
404 | What two phrases best describe the relationship of the Product Owner and the Developers? | They collaborate often so the Product Owner can make informed decisions in balancing effort and value of Product Backlog items., They collaborate often so the Developers build Increments keeping end-user and stakeholder concerns in mind.
557 | When does backlog refinement occur? | During the Sprint, in preparation for the next Sprint(s).
2061 | Which of the following best describes User Stories? | Support tools for analysis
2411 | What is the role of the Product Owner in crafting the Sprint Goal? | The PO has no role in it. This is the Development Team's responsibility.
589 | Scrum does not scale to large teams. | FALSE
439 | What outcome is expected as Scrum Teams mature? | Their definition of Done will improve to be more stringent.
455 | Who is responsible for maximizing the value of the product? | The Product Owner
2406 | A Product Owner can measure success by an increase in the team's velocity. | FALSE
421 | Which should NOT take place at the daily Scrum? | The Product Owner gives an Update.
3892 | What two attributes are optional for a Product Backlog Item? | Dependencies, Test descriptions that will prove PB Item completeness when "Done"
488 | Pick the two most important roles of the Product Owner. | Be available to the Scrum team for questions., Create and clarify valuable requirements with customers.
3924 | How can the Product Owner bring his product vision to life (select 3)? | Via the Product Backlog and iterating towards that vision every Sprint, Utilizing the underlying empirical product planning features of Scrum, Articulating the product vision to the Scrum Team and the Key Stakeholders early and often
509 | Organizational value is captured through which three evidence-based metrics? | Time to market, Current Value, Ability to innovate
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | How much of the functionality of his product is being utilized, How readily his product can be absorbed and used by his customers, Direct customer feedback
3907 | The Product Owner wants to apply some non-functional requirements to the Product. What is the best way to proceed? | Add the non-functional requirements to the DoD and check every Increment against these criteria
490 | The Agile Manifesto states that we value some items over others. Which of items are false? | Comprehensive documentation over working software.
399 | Who creates the definition of 'Done'? | The development organization (or Developers if none is available from the development organization).
501 | The Product Owner must provide transparency to the status of the Product Backlog using a: | Any means necessary to reflect work finished and work remaining.
565 | The Developers should have a lead developer to ensure the work is properly executed. | FALSE
603 | Which of the following is more important for leadership to provide when supporting their organization as they scale Scrum? | Values, principles, vision and the freedom to explore practices within the boundaries those values create.
3938 | Who is responsible for creation of the Definition of “Done”? | The Development Team
2414 | What is typical work for a Product Owner in a Sprint? Choose 2 answers. | Work with the Development Team on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
396 | A first Sprint can start before the Product Owner has a complete and exhaustive Product Backlog in place. | TRUE
400 | To what extent does technical debt limit the value a Product Owner can get from a product? Select two answers. | Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product., The velocity at which new functionality can be created is reduced when you have technical debt.
3926 | Once the Product Owner gained his Product Vision and defined the tactics of bringing this vision to life, it is a bad idea to change them before the next Product Release. | FALSE
2388 | As a Product Owner, if you had access to the following individuals, what sources might you consult with when considering the value of a product? Choose all that apply. | CEO, Sales Executive or Sales Leader, Customers and Prospects, Development Team, Market research results and analyst reports
606 | Scrum is a methodology that tells in detail how to build software incrementally. | FALSE
561 | What is the primary purpose of the Sprint Review? | Review the output of the Sprint and decide what to do next.
2443 | A Project Manager working with your Scrum Team has raised concerns about progress and money spent. What are the two best responses? | Share the current impediments., Scrum doesn't have Project Managers so disregard.
573 | What should the Product Owner focus on to ensure value is being delivered to the customer? (Pick 3) | Customer satisfaction., Percentage of functionality used by customers., Ease of use by customers.
468 | Scrum is both an iterative and incremental Agile process. | TRUE
398 | The Developers find out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? | Re-negotiate
426 | The Product Owner creates the Sprint Goal in advance of the Sprint Planning meeting. | FALSE
434 | How much work must the Developers do to a Product Backlog item it selects for the Sprint Backlog? | In conformance with the defitinion of Done.
524 | It is a best-practice in Scrum that Sprint lengths vary each Sprint as long as they don't exceed a month. | FALSE
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
550 | Which two are properties of the Daily Scrum? (2 answers) | Its location and time should remain constant., It is fifteen minutes or less in duration.
2063 | A Product Owner asked the team to work over the week-end to deliver an additional feature not planned for the sprint, in order to produce a better product. What is the appropriate response from the Scrum Master? | The Scrum Master should suggest that the Product Owner waits until the next sprint or they stop the current sprint and re-prioritize the product backlog to reflect the requested change
3911 | Who is responsible for all estimates in the Product Backlog? | The Development Team
454 | Who is responsible for maximizing the value of the product backlog? | The Product Owner.
498 | What does the 'cone of uncertainty' tell us about a Scrum project? | We have the most uncertainty about a project's lenght during the first couple of sprints.
2387 | The Product Owner must release each Increment to production. | When it makes sense.
3904 | What happens when a Sprint is cancelled? Select three. | All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The ScrumMaster
467 | An important customer wants a new feature as soon as possible, what should the Product Owner do? | Add the features to the next Sprint Planning meeting.
3951 | Every Product Backlog Item should be created by the Product Owner personally and only then the Development Team can add details to it at the PO’s discretion. | TRUE
2457 | When shoud the Product Backlog be refined? Choose 2 answers. | The PO and the Development Team do it in the actual Sprint if they haven't been able to do it in preceding Sprints., The PO and the Development Team do it in the 1-2 preceding Sprints.
569 | In what ways does the Product Owner manage the value of the product? (Pick two) | Product Backlog Order, Customer Feedback via Frequent Releases
527 | High-performing teams feature which of the following sets of characteristics? | Self-organizing, plan-driven, empowered.
544 | While under development, the environment in which a product will be used changes and emerges. What is the effect on the Product Backlog? | It evolves to reflect what the product needs to be most valuable.
446 | Who creates the Sprint Goal? | The Developers
2373 | Why would you expect a Product Owner to care about the Development Team adhering to its definition of "done"? Chosse two answers. | To have complete transparency into what has been done at the end of each Sprint., To influence the Total Cost of Ownership of the product.
472 | On Agile teams, conflict is to be avoided at all cost. | FALSE
475 | Sprint burndown charts are an efficient tracking tool because they show: | An estimate of the total work remaining for the Sprint.
3949 | What does Product Backlog management include? Select three most applicable items. | Optimizing the value of the work the Development Team performs, Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next
2365 | How should a Development Team deal with non-functional requirements? | Ensure every Increment meets them.
600 | How can the Product Owner impact technical debt? | Ask the team to improve the Definition of Done.
409 | The Product Owner manages the Product Backlog. Who is accountable for estimating the effort to complete the Product Backlog items? | The Developers. As a collective, they have a complete view of the work needed to transform Product Backlog items into Increments of product.
481 | No one, not even the Product Owner, tells the Developers how to build the product. | TRUE
3928 | Who is responsible for tracking the total work remaining in the Sprint Backlog to project the likelihood of achieving the Sprint Goal? | The Development Team
559 | Which three of the following points about the daily Scrum are TRUE? | It is time-boxed., The Scrum Master enforces the rule that only Development Team members participate., It is held at the same place and time every day.
2438 | Who should know the most about the progress toward a business objective or a release? | The Product Owner
2444 | You are a product manager with a proven track in your company. Your management has asked you to take the lead in the development of a new product. Six teams new to Scrum will build this product. What would you strive for? Select two. | The product has one Product Backlog., There should be only one Product Owner.
3953 | What are the Scrum Artifacts? Select all applicable items. | Product Backlog, Increment, Sprint Backlog
415 | The optimal length of a Sprint is? | Short enough to minimize risk to the business
452 | How do you ensure that performance requirements are addressed by the Developers? (pick 2) | Add these requirements to the Definition of Done., Add Product Backlog items to address performance.
3955 | Who should do the legwork of gathering the marketplace data for the Product Owner? | It does not matter who does the legwork
2385 | who can abnormally terminate a Sprint? | The Product Owner
2419 | The Product Backlog is ordered by: | Importance, where the most important items are at the top of all items.
3931 | When something about Scrum frustrates the Product Owner, the PO can delegate some responsibilities to the Scrum Master. | TRUE
500 | If there are multiple Scrum teams working on a product, each needs its own definition of 'Done'. | FALSE
2430 | A product's success is measured by: | The impact of customer satisfaction., The impact on revenue., The impact on cost., The impact on my performance rating.
3894 | How frequently the Product Owner should communicate and re-iterate his product vision to the Scrum Team and the Key Stakeholders? | Early and often
2447 | My role as a Product Owner focuses on which two of the following? | Keeping the stakeholders informed of the project and release status., Working with customers and stakeholder to identify the most important product requirements.
2065 | Which of the following best describes tools product owners can use to better perform their role, enhance collaboration in teams, and are especially effective when crafting a product vision and direction that hits the mark? | Visionary tracking
596 | Typically calculated is Story Points, this is the rate at which the team converts items to "Done" in a single Sprint: | Velocity
2401 | Which three of the following are timeboxed events in Scrum? | Daily Scrum, Sprint Retrospective, Sprint Planning
489 | To truly adopt Scrum, you must pick and choose which roles, artifacts, events, and rules are right for your organization. | FALSE
3905 | Who is allowed to participate in the Daily Scrum? | The Development Team
404 | What two phrases best describe the relationship of the Product Owner and the Developers? | They collaborate often so the Product Owner can make informed decisions in balancing effort and value of Product Backlog items., They collaborate often so the Developers build Increments keeping end-user and stakeholder concerns in mind.
557 | When does backlog refinement occur? | During the Sprint, in preparation for the next Sprint(s).
2061 | Which of the following best describes User Stories? | Support tools for analysis
2411 | What is the role of the Product Owner in crafting the Sprint Goal? | The PO should come to the Sprint Planning with a business objective in mind and work with the Development Team to craft the Sprint Goal based upon the forecast.
589 | Scrum does not scale to large teams. | FALSE
439 | What outcome is expected as Scrum Teams mature? | Their definition of Done will improve to be more stringent.
455 | Who is responsible for maximizing the value of the product? | The Product Owner
2406 | A Product Owner can measure success by an increase in the team's velocity. | FALSE
421 | Which should NOT take place at the daily Scrum? | The Product Owner gives an Update.
3892 | What two attributes are optional for a Product Backlog Item? | Dependencies, Test descriptions that will prove PB Item completeness when "Done"
488 | Pick the two most important roles of the Product Owner. | Be available to the Scrum team for questions., Create and clarify valuable requirements with customers.
3924 | How can the Product Owner bring his product vision to life (select 3)? | Via the Product Backlog and iterating towards that vision every Sprint, Articulating the product vision to the Scrum Team and the Key Stakeholders early and often, Making the Scrum Master bring the vision to the Scrum Team and the Key Stakeholders
509 | Organizational value is captured through which three evidence-based metrics? | Time to market, Current Value, Ability to innovate
2397 | What three things might a Scrum Product Owner focus on to ensure his product delivers value? | Minimizing changes to project scope, How readily his product can be absorbed and used by his customers, Direct customer feedback
3907 | The Product Owner wants to apply some non-functional requirements to the Product. What is the best way to proceed? | Create a new Item for every requirement in the Product Backlog
490 | The Agile Manifesto states that we value some items over others. Which of items are false? | Comprehensive documentation over working software.
399 | Who creates the definition of 'Done'? | The development organization (or Developers if none is available from the development organization).
501 | The Product Owner must provide transparency to the status of the Product Backlog using a: | Any means necessary to reflect work finished and work remaining.
565 | The Developers should have a lead developer to ensure the work is properly executed. | FALSE
603 | Which of the following is more important for leadership to provide when supporting their organization as they scale Scrum? | Values, principles, vision and the freedom to explore practices within the boundaries those values create.
3938 | Who is responsible for creation of the Definition of “Done”? | The Development Team
2414 | What is typical work for a Product Owner in a Sprint? Choose 2 answers. | Work with the Development Team on Product Backlog refinement., Collaborate with stakeholders, user communities and product managers.
396 | A first Sprint can start before the Product Owner has a complete and exhaustive Product Backlog in place. | TRUE
400 | To what extent does technical debt limit the value a Product Owner can get from a product? Select two answers. | Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product., The velocity at which new functionality can be created is reduced when you have technical debt.
3926 | Once the Product Owner gained his Product Vision and defined the tactics of bringing this vision to life, it is a bad idea to change them before the next Product Release. | FALSE
2388 | As a Product Owner, if you had access to the following individuals, what sources might you consult with when considering the value of a product? Choose all that apply. | Sales Executive or Sales Leader, Customers and Prospects, Development Team, Market research results and analyst reports
606 | Scrum is a methodology that tells in detail how to build software incrementally. | FALSE
561 | What is the primary purpose of the Sprint Review? | Review the output of the Sprint and decide what to do next.
2443 | A Project Manager working with your Scrum Team has raised concerns about progress and money spent. What are the two best responses? | Share the current impediments., Scrum doesn't have Project Managers so disregard.
573 | What should the Product Owner focus on to ensure value is being delivered to the customer? (Pick 3) | Customer satisfaction., Percentage of functionality used by customers., Ease of use by customers.
468 | Scrum is both an iterative and incremental Agile process. | TRUE
398 | The Developers find out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? | Re-negotiate
426 | The Product Owner creates the Sprint Goal in advance of the Sprint Planning meeting. | FALSE
434 | How much work must the Developers do to a Product Backlog item it selects for the Sprint Backlog? | In conformance with the defitinion of Done.
524 | It is a best-practice in Scrum that Sprint lengths vary each Sprint as long as they don't exceed a month. | FALSE
386 | What variables should a Product Owner consider when ordering the Product Backlog? | Whatever is most appropriate for the Product Owner to achieve the product's goals and to optimize the value received
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The ScrumMaster
2446 | How is management external to the Scrum Team involved in the Daily Scrum? | The Development Team self-manages and is the only management required at the Daily Scrum.
3897 | What are the three most applicable characteristics of the Product Owner? | Product Value Maximizer, Lead Facilitator of Key Stakeholder Involvement, Product Marketplace Expert
554 | Which objectives are covered as part of Sprint Planning? | Understanding what functionality the Product Owner desires within the next Sprint and figuring out how to do it.
556 | The purpose of a Sprint Retrospective is for the Scrum Team to: | Determine what to stop doing, start doing, and continue doing.
2061 | Which of the following best describes User Stories? | Use Cases
2457 | When shoud the Product Backlog be refined? Choose 2 answers. | The PO and the Development Team do it in the 1-2 preceding Sprints., The PO and the Development Team do it in the actual Sprint if they haven't been able to do it in preceding Sprints.
3957 | What provides guidance to the Development Team on why it is building the Increment? | The Sprint Goal
2410 | Which three of the following are true about Scrum? | Scrum is based on empirical process control theory., Scrum is a framework for developing and sustaining complex products., Each component of Scrum serves a specific purpose, and is essential to Scrum's success and your usage of Scrum to develop complex products.
423 | The Product Owner does not have to be a single person but may be a committee or a shared responsibility between multiple individuals. | FALSE
2396 | For the purpose of transparency, when does Scrum say a new increment of working software must be available? | At the end of every Sprint.
600 | How can the Product Owner impact technical debt? | Ask the team to improve the Definition of Done.
511 | When is the Sprint Backlog finalized? | During the Sprint
403 | What two things should be done if the Product Owner is unavailable? | Within the Sprint, the Developers make the best decisions possible to assure progress toward the Sprint Goal, re-aligning with the Product Owner once he/she is available again., In a permanent state of unavailability, a new Product Owner needs to be appointed. Development efforts without a Product Owner are not employing Scrum.
3917 | How does Definition of “Done” help to the Scrum Team? Select the three most applicable items. | Guides the Development Team in knowing how many Product Backlog items it can select during a Sprint Planning, DoD helps in inspection and adaptation, DoD ensures artifact transparency
399 | Who creates the definition of 'Done'? | The development organization (or Developers if none is available from the development organization).
489 | To truly adopt Scrum, you must pick and choose which roles, artifacts, events, and rules are right for your organization. | FALSE
2448 | What are three ways Scrum promotes self-organization? | By preventing stakeholders from entering the development room., By the Development Team decinding what work to do in a Sprint., By being a lightweight framework.
2382 | A done Increment is valuable if: (Choose two answers) | It is likely to increase customer satisfaction., It reduces long-term operational costs.
2453 | What are criteria to order Product Backlog items? | All of the answers.
2367 | What are two responsibilities of testers in a Development Team? Choose 2 answers. | Everyone in the Development team is responsible for quality, Scrum has no "tester" role
2399 | As the Sprint Planning meeting progresses, the Development Team sees that the workload is greater than they can handle. Which two are valid actions? | Remove or change selected Product Backlog items., The Development Team ensures that the Product Owner is aware, starts the Sprints, and monitors progress.
540 | Which three activities will a Product Owner likely engage in during a Sprint? | Work with the stakeholders., Provide feedback., Answer questions from the Developers about items in the current Sprint.
473 | Backlog Grooming and Backlog Refinement are the same thing. | TRUE
390 | What two things best help the Product Owner manage the value of a product? | The order of the Product Backlog., Validating assumptions of value through frequent releases.
3945 | What is the essence of Scrum? Select the most appropriate option. | A small team of people that is highly flexible and adaptive
452 | How do you ensure that performance requirements are addressed by the Developers? (pick 2) | Add Product Backlog items to address performance., Add these requirements to the Definition of Done.
433 | The Product Owner is responsible for the definition of Done. | FALSE
3933 | Who identifies the Key Stakeholders for the Product? | The Product Owner
398 | The Developers find out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? | Rework the selected Product Backlog items with the Developers to meet the Sprint Goal.
2430 | A product's success is measured by: | The impact on my performance rating., The impact on cost., The impact of customer satisfaction., The impact on revenue.
572 | A key measure of success for the Product Owner to track is the development team's velocity. | FALSE
402 | What is the Product Owner accountable for in Scrum? | Creating and sustaining a Product Backlog that maximizes value and represents the needs of the stakeholders.
3953 | What are the Scrum Artifacts? Select all applicable items. | Sprint Backlog, Product Backlog, Increment
599 | The total cost of ownership (TCO) for a product is the sum of all investments required to design, develop, run and support the product. | TRUE
3898 | The Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment. | TRUE
387 | What preconditions must be fulfilled in order to allow Sprint Planning to begin? | There are no such preconditions
2434 | Who creates a P roduct Backlog item's estimate? | The Devlopment Team, alone.
3932 | What does Burn-down Chart show? | How much work remains till the end of the Sprint
2392 | Which output from Sprint Planning provides the Development Team with a target and overarching direction for the Sprint? | The Sprint Goal
435 | Which of the following reflects Scrum's expectation of 'validated learning'? | Customer feedback after frequent releases.
424 | Who updates work remaining during the Sprint? | The Developers
3934 | All the Scrum Teams working on the same product should have the same Sprint length. | FALSE
430 | What happens if the customer no longer wants the feature that the Sprint Goal intended to meet? | The Product Owner should cancel the Sprint.
3903 | Who is responsible for promoting and supporting Scrum? Select the best choice. | The Scrum Master
2380 | How small should a 'ready' Product Backlog item be? | No longer than one day.
2384 | Who is responsible for tracking the remaining work of the Sprint? | The Development Team
426 | The Product Owner creates the Sprint Goal in advance of the Sprint Planning meeting. | FALSE
3922 | Could the Product Owner and the Scrum Master be a part of the Development Team? | TRUE
502 | Which of the following sets of tools is least likely to be utilized by a Scrum Team? | Smart board, card wall
397 | Learning turns into 'validated learning' when assumptions and goals can be assessed through results. What is a key way for a Product Owner to apply validated learning? | Release an Increment to the market to learn about the business assumptions built into the product.
2409 | Which answer best describes the topics covered in Sprint Planning? | What to do and who will do it.
552 | The correct sequence of events in using Scrum framework is as follows: | Sprint Planning, Sprint, Daily Scrum, Sprint Review, and Sprint Retrospective.
509 | Organizational value is captured through which three evidence-based metrics? | Time to market, Current Value, Ability to innovate
611 | The Product Owner makes sure the right stakeholders are invited to the Sprint Review. They might have important instructions for Product improvements. | TRUE
503 | When was Scrum first introduced? | In 1995 at a conference presentation.
2441 | Multiple Scrum Team working on the same product or system all select work from the same Product Backlog. | TRUE
429 | The person responsible for the Scrum process, making sure it is used correctly and maximizing its benefit: | Scrum Master
2070 | Which of the following is NOT an example of a good User Story in the context of an online job postings site? | C++ will be used to write the software
3954 | Product Backlog Refinement … | Is the act of adding detail, estimates, and order to Product Backlog items, Is an ongoing process, Takes no more than 10% of the capacity of the Development Team
Select the three most applicable sentence endings.
3926 | Once the Product Owner gained his Product Vision and defined the tactics of bringing this vision to life, it is a bad idea to change them before the next Product Release. | FALSE
3921 | How long does the Product Backlog exists? | While the Product exists
2442 | When many Development Teams are working on a single product, what best describes the definition of 'Done'? | All Development Teams must have a definition of 'Done' that makes their combined work potentialy releasable.
3909 | Who is allowed to make changes in the Product Backlog? | The Product Owner, The Development Team, but with permission of the Product Owner
461 | Which is a report of all the work that is 'Done?' | Burndown chart
451 | What are the mandatory prerequisites to the Sprint Planning meeting? | There are no mandatory prerequisites.
519 | If a customer really wants a feature added to a Sprint, how should the Developers respond? | Ask the Product Owner to work with the customer.
431 | Who is NOT part of the Scrum Team (Choose 2)? | Customer, The Development Team
541 | Every Scrum Team must have a Product Owner and Scrum Master. | True. Outcomes are affected by their participation and availability.
2404 | What is the time-box for the Sprint Planning meeting? | 8 hours for a monthly Sprint
505 | The backlog is ordered by: | The needs of the Product Owner
427 | An iteration takes place in a time frame with specific start and end dates, called a time-box. Which of the following is NOT an advantage of time-boxing? | Helps control technical debt.
520 | Software dependencies can influence how the product owner orders Product Backlog items. | FALSE
475 | Sprint burndown charts are an efficient tracking tool because they show: | An estimate of the total work remaining for the Sprint.
3963 | Who is responsible for crafting the Sprint Goal at the Sprint Planning? | The Development Team
391 | In order to make investment decisions, the Product Owner is likely to look at the Total Cost of Ownership (TCO) of the product being built. What costs will a Product Owner take into account? | All investments required to conceive, develop, operate and maintain the product.
2429 | Who is responsible for engaging the stakeholders? | The Product Owner.
442 | Who must do all of the work to ensure the Product Backlog items conform to the definition of “Done”? | The Developers
2440 | Who should make sure everyone on the Development Team does his or her tasks for the Sprint? | The Development Team
2374 | Which Scrum Values are exhibited by not building Product Backlog items that have low business value? | Courage, Focus, Respect
453 | What is the most effective way to order the Product Backlog? | It is up to the Product Owner to decide.
2369 | What does it mean to say that an event has a time-box? | The event can take no more than a maximum amount of time.
596 | Typically calculated is Story Points, this is the rate at which the team converts items to "Done" in a single Sprint: | Burndown rate
3919 | Which Key Value Areas (KVA) categories should the Product Owner consider to measure and track the creation and delivery of value to the market place (select three)? | Ability to Innovate, Current Value, Time-to-Market
3967 | How frequently product releases should occur? | Frequently enough to eliminate the risk that the product’s value will get out of line with the marketplace
573 | What should the Product Owner focus on to ensure value is being delivered to the customer? (Pick 3) | Customer satisfaction., Cost per feature delivered., Percentage of functionality used by customers.
403 | What two things should be done if the Product Owner is unavailable? | In a permanent state of unavailability, a new Product Owner needs to be appointed. Development efforts without a Product Owner are not employing Scrum., Within the Sprint, the Developers make the best decisions possible to assure progress toward the Sprint Goal, re-aligning with the Product Owner once he/she is available again.
3929 | What factors should be considered by the Product Owner in the release decision (select four)? | The amount of work remaining toward the Sprint Goal, Approval of the Key Stakeholders, The risk that the product’s value can get out of line with the marketplace, Does the Increment meet the Definition of “Done”?
532 | When maintaining the product backlog, this role represents the interests of the stakeholders, and ensures the value of the work completed: | Product Owner
2375 | During a Sprint Retrospective, for what is the Scrum Master responsible? | Participating as a Scrum team member and facilitating as requested or needed.
457 | The Product Backlog should be transparent to the entire organization. | TRUE
2381 | A Scrum team is only allowed to meet with stakeholders during Sprint Review. | FALSE
3918 | When a product grows, it is quite possible that the PO will get help from other Product Managers and others in the organization who interact regarding the customer facing activities and knowledge of the product marketplace. Is it a good idea for the PO to proxy or outsource some of their PO Scrum Team duties to these people (for example, Scrum Team facing duties)? | FALSE
465 | The sprint Retrospective: | Is intended to promote continuous process improvements.
2398 | Why is the Daily Scrum held at the same time and the same place? | The consistency reduces complexity.
2052 | You are a Product Owner working on an agile software development project and you have brought all the Scrum team members together for the first Iteration Planning meeting. You read the user stories to the team, and they have provided estimates to complete these user stories. You have promised to leave them alone during the iteration to get the work done and they have agreed to complete the work 100% according to the definition of done. What is this an example of? | Reciprocal commitment
491 | Which one is NOT a Pillar of Scrum? | Empiricism
3952 | Who has the “last say” on the order of items in the Product Backlog? | The Product Owner
2064 | The Product Owner of your project is absent due to a planned vacation. Who should assume the Product Owner's responsibilities at a sprint planning meeting? | The team
3944 | Select the five Scrum Values. | Respect, Courage, Focus, Openness, Commitment
2418 | Sprint Reviews are an opportune time to collect customer feedback. | TRUE
2382 | A done Increment is valuable if: (Choose two answers) | It is likely to increase customer satisfaction., It has all the fetures that the Product Owner wanted in that Sprint.
451 | What are the mandatory prerequisites to the Sprint Planning meeting? | There are no mandatory prerequisites.
396 | A first Sprint can start before the Product Owner has a complete and exhaustive Product Backlog in place. | TRUE
458 | The optimum size of the Scrum Team is: | Less than 10 people
429 | The person responsible for the Scrum process, making sure it is used correctly and maximizing its benefit: | Scrum Manager
2372 | If two Scrum Teams are added to the development of a product that previously had only one Scrum Team, what will be the immediate impact on the productivity of the original Scrum Team? | Its productivity is likely to decrease.
412 | The value delivered by a product can only be determined by revenue. | FALSE
2062 | In an Agile project, the Product Owner: | Represents the stakeholders and the business
401 | How important is it for a Product Owner to order Product Backlog items by value points? | It is a good practice, keeping in mind that market reception is the best measure of value.
557 | When does backlog refinement occur? | During the Sprint, in preparation for the next Sprint(s).
464 | What is the primary tool of the Product Owner for measuring product progress? | Product Backlog
3909 | Who is allowed to make changes in the Product Backlog? | The Product Owner, The Development Team, but with permission of the Product Owner
2425 | A new developer is having continuing conflicts with existing Development Team members and creating a hostile environment. If necessary, who is reponsible for removing the team member? | The Development Tem is responsible, and may need help from the Scrum Master.
2406 | A Product Owner can measure success by an increase in the team's velocity. | FALSE
3968 | The Sprint Review is just a demo of the Product Backlog items completed during a Sprint. Do you agree? | No, the Sprint Review contains much more activities
440 | The Project Manager plays the following role in Scrum: | There is no project manager role in Scrum.
3954 | Product Backlog Refinement … | Takes no more than 10% of the capacity of the Development Team, Is the act of adding detail, estimates, and order to Product Backlog items, Is an ongoing process
Select the three most applicable sentence endings.
3948 | Product Backlog Refinement practice focuses on Items for upcoming Sprints, not the current Sprint in progress. True or false? | TRUE
2412 | Which of the following practices might help the Product Owner minimize waste in developing and sustaining the Product Backlog? Choose 2 answers. | Write or cause Product Backlog items to be written clearly, and with a little ambiguity as possible., Only fully describe Product Backlog items when it seems sure that they are likely to be implemented.
414 | How can a Product Owner use time-boxed Sprints to obtain feedback from users and the market? | Through frequent delivery of Increments of the product into the market.
3939 | Who is responsible for the monitoring of the remaining work towards the Project Goal? | The Product Owner
443 | The feedback from the Sprint Review impacts the next Sprint planning meeting. | TRUE
2395 | What are two good ways for a Scrum Team to ensure security concerns are satisfied? | Have the Scrum Team create Product Backlog items for each concern., Add security concerns to the definition of "Done".
487 | A 4-hour Sprint Planning meeting is typical for a Sprint or Iteration that is how long? | Two weeks
406 | A Product Owner is entitled to postpone the start of a new Sprint after the conclusion of a previous Sprint for the following reason: | There is no acceptable reason. A new Sprint starts immediately after the conclusion of the previous Sprint.
397 | Learning turns into 'validated learning' when assumptions and goals can be assessed through results. What is a key way for a Product Owner to apply validated learning? | Accept an Increment at the Sprint review to learn about the forecast of functionality that was developed.
388 | The process of regular inspection and adaptation employs knowledgeable and skilled inspectors. What are two ways in which the Product Owner takes the lead in the inspection process? | At the Sprint Review the Product Owner shares the current state of Product Backlog, which, combined with the inspection of the Increment, leads to an updated Product Backlog., The Product Owner invites stakeholders to the Sprint Review to learn how the current state of the marketplace influences what is the most valuable thing to do next.
534 | Which of the following statements is NOT true? | The Product Backlog is complete when the final product Increment is considered Done.
472 | On Agile teams, conflict is to be avoided at all cost. | FALSE
3892 | What two attributes are optional for a Product Backlog Item? | Test descriptions that will prove PB Item completeness when "Done", Value
2370 | Which two (2) metrics will help a Product Owner establish that value is being delivered? | Customer satisfaction, Time to market
481 | No one, not even the Product Owner, tells the Developers how to build the product. | TRUE
3902 | Where Scrum can be used? Check all the applicable items. | Development of almost everything we use in our daily lives as individuals and societies, Research and identifying of viable markets, technologies, and product capabilities, Managing the operation of an organization, Development of software and hardware, Development and sustaining of Cloud and other operational environments, Development of products and enhancements
2417 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Which two measures ensure that the Product Backlog is transparent? | The Product Backlog is ordered., The Product Backlog is available to all stakeholders.
2379 | What is Product Owner work that a Product Owner might delegate? | Writing User Stories
2367 | What are two responsibilities of testers in a Development Team? Choose 2 answers. | Everyone in the Development team is responsible for quality, Scrum has no "tester" role
400 | To what extent does technical debt limit the value a Product Owner can get from a product? Select two answers. | The velocity at which new functionality can be created is reduced when you have technical debt., Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product.
387 | What preconditions must be fulfilled in order to allow Sprint Planning to begin? | There are no such preconditions
490 | The Agile Manifesto states that we value some items over others. Which of items are false? | Comprehensive documentation over working software.
2383 | Who owns the Sprint Backlog? | The Development Team
521 | The Product Owner is not required at the Daily Scrum. | TRUE
570 | A Product Owner should have a sigle metric to measure the value it is delivering each Sprint. | FALSE
516 | Which does a self-organizing Scrum Team choose? | How to best accomplish its work.
389 | The Product Owner's authority to change and update the Product Backlog is unlimited, except for: | Nothing. The entire organization must respect a Product Owner's decisions.
523 | All of the following are inputs to the Sprint Planning meeting EXCEPT: | Team Velocity
2373 | Why would you expect a Product Owner to care about the Development Team adhering to its definition of "done"? Chosse two answers. | To influence the Total Cost of Ownership of the product., To have complete transparency into what has been done at the end of each Sprint.
423 | The Product Owner does not have to be a single person but may be a committee or a shared responsibility between multiple individuals. | FALSE
2393 | Which two of the following are true about the Scrum Master role? | The Scrum Master helps those outside the team interact with the Scrum Team., The Scrum Master teaches the Development Team to keep the Scrum meetings to their timebox.
459 | Which of the following three statements are true about the Product Owner role? | The Product Owner is one person., The Product Owner is accountable for ordering the Product Backlog., The Product Owner can be influenced by a committee.
2058 | The Product Owner is responsible for: | ROI of the project
2433 | In order to maximize the value of the product, a Product Owner needs awareness of the following: | All of the answers
526 | Stakeholders can interact with the Scrum team in which two ways? | Via interactions with the Product Owner., At the Sprint Review.
519 | If a customer really wants a feature added to a Sprint, how should the Developers respond? | Ask the Product Owner to work with the customer.
2056 | What are the duties of a Product Owner on an Agile team? | Coordinate the team and make sure they are working on the features important to the customer
499 | If multiple Teams are working on the same product, how should they write their definition of 'Done'? | There should be a single definition of Done for all Teams.
507 | The Product Owner should be with the Developers full time. | FALSE
386 | What variables should a Product Owner consider when ordering the Product Backlog? | Whatever is most appropriate for the Product Owner to achieve the product's goals and to optimize the value received
2070 | Which of the following is NOT an example of a good User Story in the context of an online job postings site? | C++ will be used to write the software
424 | Who updates work remaining during the Sprint? | The Developers
544 | While under development, the environment in which a product will be used changes and emerges. What is the effect on the Product Backlog? | It evolves to reflect what the product needs to be most valuable.
507 | The Product Owner should be with the Developers full time. | FALSE
556 | The purpose of a Sprint Retrospective is for the Scrum Team to: | Determine what to stop doing, start doing, and continue doing.
2374 | Which Scrum Values are exhibited by not building Product Backlog items that have low business value? | Focus, Economic Value Added
3909 | Who is allowed to make changes in the Product Backlog? | The Development Team, but with permission of the Product Owner, The Product Owner
525 | The Product backlog is ordered by: | Importance / Value
3899 | What could be a source of requirements for any changes to be made to the product? | The Product Backlog
406 | A Product Owner is entitled to postpone the start of a new Sprint after the conclusion of a previous Sprint for the following reason: | There is no acceptable reason. A new Sprint starts immediately after the conclusion of the previous Sprint.
2058 | The Product Owner is responsible for: | ROI of the project
457 | The Product Backlog should be transparent to the entire organization. | TRUE
3946 | If an item in the Sprint Backlog cannot be finished by the end of the Sprint (it turned out there is a lot more work to do than was estimated), the Sprint is cancelled. | FALSE
513 | The product Increment must be released to production at the end of each Sprint. | FALSE
413 | How does an organization know that a product built through Scrum is successful? | By releasing often, and updating key performance indicators (KPIs) on value after every release and feeding this information back into work on the Product Backlog.
558 | Scrum is a container for other techniques and methodologies. | TRUE
2390 | What is the purpose of a Sprint Review? | To inspect the product increment with the stakeholders and collect feedback on next steps
471 | If the Product Backlog is not ready for Sprint Planning, what happens? | Identify enough work for the first day and set up a second Sprint Planning meeting when the Product Backlog is ready.
3892 | What two attributes are optional for a Product Backlog Item? | Dependencies, Value
2421 | The PO should have a complete and exhaustive Product Backlog before the first Sprint can start? | FALSE
589 | Scrum does not scale to large teams. | FALSE
538 | When is a Product Backlog item considered complete? | The item has no work remaining that must still be done before it can be used by its end user.
452 | How do you ensure that performance requirements are addressed by the Developers? (pick 2) | Add these requirements to the Definition of Done., Add Product Backlog items to address performance.
2426 | Product Owners must create clear and unambiguous acceptance criteria for each Product Backlog item before it may be selected in Sprint Planning. | FALSE
526 | Stakeholders can interact with the Scrum team in which two ways? | At the Sprint Review., Via interactions with the Product Owner.
512 | Who hires the Product Owner? | Whoever is accountable for the product ROI
613 | How often should customer satisfaction be measured? | Frequently.
532 | When maintaining the product backlog, this role represents the interests of the stakeholders, and ensures the value of the work completed: | Product Owner
3966 | Who is allowed to tell the Development Team to work from a set of requirements? | The Product Owner, The Key Stakeholders
2369 | What does it mean to say that an event has a time-box? | The event can take no more than a maximum amount of time.
392 | Must the Product Owner be present at the Sprint Retrospective? | It is mandatory. The Sprint Retrospective is an opportunity for the Scrum Team to assess its performance and improve itself.
487 | A 4-hour Sprint Planning meeting is typical for a Sprint or Iteration that is how long? | Two weeks
410 | It is mandatory for the Product Owner to monitor and share progress of Product Backlog through: | A Product or Release burn-down chart.
2398 | Why is the Daily Scrum held at the same time and the same place? | The consistency reduces complexity.
3940 | What is the Increment? | The sum of all the Product Backlog items completed during the Sprint and the value of the increments of all previous Sprints
516 | Which does a self-organizing Scrum Team choose? | How to best accomplish its work.
574 | How complete should the Sprint Backlog be at the end of the Sprint Planning meeting? | Enough to ensure there is work for the first few days of the Sprint.
2413 | When should the Product Owner update the project plan? | Scrum forbids having a project plan.
435 | Which of the following reflects Scrum's expectation of 'validated learning'? | Customer feedback after frequent releases.
495 | No one but the Scrum Team attends the Sprint Planning meeting. | FALSE
2371 | Which two things should the Development Team do during the first Sprint? | Create an Increment of potentially releasable software., Develop at least one piece of functionality.
561 | What is the primary purpose of the Sprint Review? | Review the output of the Sprint and decide what to do next.
2377 | You are a product manager with a proven track record in your company. Your management has asked you to take the lead in the development of a new product. Six teams new to Scrum will build this product. What would you strive for? Select two. | The product has one Product Backlog., There should be only one Product Owner.
599 | The total cost of ownership (TCO) for a product is the sum of all investments required to design, develop, run and support the product. | TRUE
3955 | Who should do the legwork of gathering the marketplace data for the Product Owner? | The Product Owner
2440 | Who should make sure everyone on the Development Team does his or her tasks for the Sprint? | The Product Owner
2067 | Why are the top 20% of items of a Product Backlog the most important to accomplish? | Because according to the Pareto rule, 80 percentage of the value comes from 20 percentage of the work
494 | The Product Backlog is baselined at the start of the project and not changed for at least three Sprints. | FALSE
400 | To what extent does technical debt limit the value a Product Owner can get from a product? Select two answers. | Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product., The velocity at which new functionality can be created is reduced when you have technical debt.
2402 | A Product Owner with multiple teams working on one product should maintain separate Product Backlogs for each team. | FALSE
3953 | What are the Scrum Artifacts? Select all applicable items. | Product Backlog, Increment, Sprint Backlog
2379 | What is Product Owner work that a Product Owner might delegate? | Writing User Stories
440 | The Project Manager plays the following role in Scrum: | There is no project manager role in Scrum.
470 | There are 5 teams working on a product, how many Product Owners would there be? | 1
568 | Product Backlog Items should always be expressed as User Stories. | FALSE
540 | Which three activities will a Product Owner likely engage in during a Sprint? | Work with the stakeholders., Provide feedback., Answer questions from the Developers about items in the current Sprint.
2057 | Scrum defines four reports to be prepared at the end of each sprint. Which of the following roles have the responsibility of creating these reports? I. Product Owner II. Team members III. ScrumMaster | I & III
2407 | What activities would a Product Owner typically undertake in the phase between the end of the current Sprint and the start of the next Sprint? | There are no such activities. The next Sprint starts immediately after the current Sprint.
519 | If a customer really wants a feature added to a Sprint, how should the Developers respond? | Ask the Product Owner to work with the customer.
2051 | A Persona used within an Agile user story can be thought of as: | An imaginary representation of a user role
489 | To truly adopt Scrum, you must pick and choose which roles, artifacts, events, and rules are right for your organization. | TRUE
562 | When is a Product Backlog item 'Ready' for the Sprint? | It can be Done in one Sprint.
542 | Which technique is the LEAST productive way for the Scrum Master to ensure that the Developers communicates effectively with the Product Owner? | Monitor communications between them.
462 | A new Sprint starts immediately following the previous Sprint. | TRUE
2458 | When does the second Sprint start? | Immediately after the first Sprint.
443 | The feedback from the Sprint Review impacts the next Sprint planning meeting. | TRUE
2459 | Which statement best describes the Sprint Backlog as outcome of the Sprint Planning? | It is a complete list of all work to be done in a Sprint.
2068 | The term "pigs" is used to refer to which of the following roles in a Scrum project? | The company CEO
2387 | The Product Owner must release each Increment to production. | When it makes sense.
2063 | A Product Owner asked the team to work over the week-end to deliver an additional feature not planned for the sprint, in order to produce a better product. What is the appropriate response from the Scrum Master? | The Scrum Master should suggest that the Product Owner waits until the next sprint or they stop the current sprint and re-prioritize the product backlog to reflect the requested change
3947 | Who is allowed to change the Sprint Backlog during the Sprint? | The Development Team
434 | How much work must the Developers do to a Product Backlog item it selects for the Sprint Backlog? | As much as can be accomplished in the timebox.
2453 | What are criteria to order Product Backlog items? | Value of Product Backlog items.
403 | What two things should be done if the Product Owner is unavailable? | In a permanent state of unavailability, a new Product Owner needs to be appointed. Development efforts without a Product Owner are not employing Scrum., Within the Sprint, the Developers make the best decisions possible to assure progress toward the Sprint Goal, re-aligning with the Product Owner once he/she is available again.
2434 | Who creates a P roduct Backlog item's estimate? | The Development Team after clarifying requirements with the Product Owner.
430 | What happens if the customer no longer wants the feature that the Sprint Goal intended to meet? | The Product Owner should cancel the Sprint.
2435 | A product's success is measured by: | The impact on customer satisfaction., The impact on revenue., The impact on cost.
3912 | How does the Scrum Master help the Product Owner? Select the three most appropriate answers. | Facilitating Scrum events as requested or needed, Leading and coaching the organization in its Scrum adoption, Understanding product planning in an empirical environment
2070 | Which of the following is NOT an example of a good User Story in the context of an online job postings site? | C++ will be used to write the software
469 | Which statement is least accurate when providing a definition of 'Done'? | It is defined by the Scrum Master.
2451 | The CEO asks the Development Team to add a "very important" item to a Sprint that is in progress. What should the Development Team do? | Inform the Product Owner so he/she can work with the CEO.