## Sheet1
corrigé le 16/03 15h18 | The primary target of the PO is the VALUE. PB : Product Backlog. A new sprint starts immediately after the previous sprint. DOD : Definition of done. Ne jamais choisir comme réponses "hardening" et "tester".
The value | Its management by order the PB ans validating assumptions. Is not only determined by revenue. To make investment, all required to conceive and develop. With technical debt > velocity reduced > greater budget. The PO is responsible for the ROI (Return On Investment), he monitors by any practice. The project plan updated (by the PO) as new information and insights emerge. The TCO (Total Cost of Ownership) is the sum of all investments required.
Points | Ultimate way to predict the value. Developers are accountable for estimates.
Increment | To learn about the forecast, the sum of all PO items.
Product backlog | Criteria to order : Value, dependencies to other and between. Difficulty to build : re-negociate. Ordering by anythings that informs. Updated only during PB refinement. Not ready for sprint planning : cancel the sprint. Changes by the PO and by the developers (with PO permission). NEVER BASELINED. It is the only source of requirements for any changes to be made. PB often include test descriptions. The PO must create acceptance criteria.
Scrum | Successful by releasing frequently/often. Timeboxes help minimize risk. Container for other techniques and methodologies. VALUES : Courage, openness, focus, commitment, respect (all affected by lack of trust). Validated learning : customer feedback.
Sprint | Typically : collaborate with stakeholders and work with the developers. To allow sprint planning : PB, product goal. Sprint retrospective : what to stop and start doing, mandatory for the PO. 3 activities of the PO : work (provide feedback) with the stackholders, answer questions.
Organization | Must respect the PO's decisions. It creates the DOD.
Divers | Legwork of gathering : it does not matter. A persona : An imaginary representation of a user role. Least productive : act as a go-between. Pigs : the team. Product succes : customer satisfaction, revenue, cost.